## Raw_Data
Issue_ID | Created_Date | Resolved_Date | Assignee | Milestone | Source | Sprint_ID | Sprint_Start_Date | Sprint_End_Date | Completion_Time | Standardized_Status | Issue_Type | Completion_Flag | Data_Quality_Flag | Planned_Flag | Completed_In_Sprint_Flag | Carry_Forward_Flag
36279 | 01-01-2024 | 01-01-2024 | Unassigned |  | GitHub | Sprint_01 | 01-01-2024 | 14-01-2024 | 0.07 | Done | Bug | 1 | Valid | 1 | 1 | 0
KAFKA-101 | 01-01-2024 | 05-01-2024 | jdoe | 3.6.0 | Apache | Sprint_01 | 01-01-2024 | 14-01-2024 | 4.21 | Done | Bug | 1 | Valid | 1 | 1 | 0
36281 | 01-01-2024 |  | Unassigned |  | GitHub | Sprint_01 | 01-01-2024 | 14-01-2024 |  | To Do | Bug | 0 | Valid | 1 | 0 | 0
36283 | 01-01-2024 |  | Unassigned |  | GitHub | Sprint_01 | 01-01-2024 | 14-01-2024 |  | To Do | Other | 0 | Valid | 1 | 0 | 0
36284 | 02-01-2024 |  | Unassigned |  | GitHub | Sprint_01 | 01-01-2024 | 14-01-2024 |  | To Do | Other | 0 | Valid | 1 | 0 | 0
36288 | 02-01-2024 |  | Unassigned |  | GitHub | Sprint_01 | 01-01-2024 | 14-01-2024 |  | To Do | Other | 0 | Valid | 1 | 0 | 0
KAFKA-102 | 02-01-2024 |  | asmith | 3.7.0 | Apache | Sprint_01 | 01-01-2024 | 14-01-2024 |  | To Do | Feature | 0 | Valid | 1 | 0 | 0
36298 | 02-01-2024 |  | Unassigned |  | GitHub | Sprint_01 | 01-01-2024 | 14-01-2024 |  | To Do | Other | 0 | Valid | 1 | 0 | 0
36302 | 02-01-2024 | 03-01-2024 | Unassigned |  | GitHub | Sprint_01 | 01-01-2024 | 14-01-2024 | 0.41 | Done | Other | 1 | Valid | 1 | 1 | 0
KAFKA-103 | 03-01-2024 | 15-01-2024 | jdoe | 3.6.0 | Apache | Sprint_01 | 01-01-2024 | 14-01-2024 | 12.12 | Done | Tech Debt | 1 | Valid | 1 | 0 | 1
36315 | 04-01-2024 |  | Unassigned |  | GitHub | Sprint_01 | 01-01-2024 | 14-01-2024 |  | To Do | Bug | 0 | Valid | 1 | 0 | 0
KAFKA-104 | 10-01-2024 | 12-01-2024 | asmith | 3.6.0 | Apache | Sprint_01 | 01-01-2024 | 14-01-2024 | 2.08 | In Progress | Bug | 0 | Valid | 1 | 0 | 0
KAFKA-105 | 15-01-2024 |  | rjones | 3.7.0 | Apache | Sprint_02 | 15-01-2024 | 28-01-2024 |  | To Do | Other | 0 | Valid | 1 | 0 | 0

## Sprint_Summary
Sprint_ID | Total_Issues | Planned_Work | Completed_Work | Completed_In_Sprint | Spillover | Validation_Check
Sprint_01
Sprint_02

## Metrics_Calculation
Sprint_ID | Commitment_Reliability | Spillover_Rate | Risk_Severity | Data_Strength_Flag | Adjusted_Risk_Label
Sprint_01
Sprint_02

## Dashboard_Base
ELITE ANALYTICS: DELIVERY RISK FRAMEWORK
Sprint Performance Table | Executive Summary
Sprint_01 | Weighted Avg Commitment
Sprint_02 | Weighted Avg Spillover
High Risk Sprint Count
Worst Reliable Sprint
Trend (Reliable Data Only)
Error Count
Key Insight:
Reliable sprint data indicates critically low delivery predictability, suggesting systemic overcommitment and poor execution discipline.
Recommended Actions:
* Reduce sprint scope by 20–30%
* Limit concurrent work (WIP)
* Introduce mid-sprint progress tracking